## Slide 1
PROJECT MANAGEMENT
TRAINING FOR ATHLETE LEADERS

## Slide 2
Project Management Training for Athlete Leaders
PART 1 | Welcome and Project Idea Building
2 hours | Define key words to know Introduce five phases of Project Management Utilize “Building Your Project Idea Assessment” to select a Project best for you and your community.
PART 2 | Planning and Managing your Project
2 hours | Develop achievable project goals Apply the five phases of project management to your goals Gain skills to tell your project story

## Slide 3
PART 1:
WELCOME AND PROJECT IDEA BUILDING

## Slide 4
Goal and Objectives of the Training
The Objectives of this training are:
Learn how to identify a problem or gap in your Program or community and design a project to address it.
Review key words of project management.
Learn and understand the five phases of project management.
Explore tools to use during each phase of project management.
Develop a project plan that outlines clear steps, resources, and timelines to bring your idea to life.

## Slide 5
Key words and definitions

## Slide 6
Project management empowers you to turn big ideas into action and make a lasting impact in your program or your community. By learning to plan, organize, and execute effectively, you’ll gain the skills to lead with confidence, inspire people around you, and create meaningful change in your community.
Introduction and Welcome
Why Project Management Training?

## Slide 7
Key words and definitions
What is a Project?
A project is a temporary activity with a definite beginning and end. It creates or produces a unique product, service or result.
A project is NOT a task that you do regularly like attend practice, fill out a timesheet at work, etc.
Project

## Slide 8
Project examples
Project idea #1
Create a project to recruit, train, and engage athletes under the age of 25, increasing the percentage of this age group from 35% to 50% in 5 years.
Key words and definitions
Project
What is a Project?
Notes: Ask learners to think of any projects they’ve been involved in—at school, work, or in their personal lives—and invite a few to share. Encourage mentors to do the same to set an example. Then, ask learners to think about projects related to Special Olympics, like events or initiatives, and discuss how planning and teamwork played a role. Invite participants to share a few examples and then share the examples on the screen:
    Project idea #1: Your Special Olympics Program notices that only 35% of their athletes are under the age of 25. They research why by talking to people in their Program and people in other sports organizations for people with disabilities to understand what their Program is missing. They want to increase the number of athletes under the age of 25 and create a project to recruit, train, and engage younger athletes and find coaches to work with them.

## Slide 9
Project examples
Project idea #1
Create a project to recruit, train, and engage athletes under the age of 25, increasing the percentage of this age group from 35% to 50% in 5 years.
Key words and definitions
Project
What is a Project?
Project idea #2
Create a project to increase the number of volleyball teams by 50% to 40 teams over the next 3 years.
Notes: Project idea #2: Your Special Olympics Program used to have more than 50 teams that competed in volleyball during the season, but that number has shrunk to only 20 teams that still compete over the past 5 years. Your SO Program asks former SO volleyball athletes and coaches why they have stopped playing and creates a project to increase the number of volleyball teams by 50% to 40 teams over the next 3 years.

## Slide 10
The application of knowledge, skills, tools, and techniques to project activities to meet the project requirements.
Key words and definitions
Project Management
What is Project Management?

## Slide 11
The application of knowledge, skills, tools, and techniques to project activities to meet the project requirements.
Key words and definitions
Project Management
What is Project Management?
Let’s break that down:
Using what you know, the right tools, and helpful skills to get things done and reach what you want to achieve in the project.

## Slide 12
What is a
Project Manager?
Key words and definitions
Team roles and responsibilities

## Slide 13
What is a
Project Manager?
An individual who is responsible for ensuring the project is completed on time, within budget, and on schedule.
This is YOU!
Key words and definitions
Team roles and responsibilities

## Slide 14
What is a
Team Member?
Key words and definitions
Team roles and responsibilities

## Slide 15
What is a
Team Member?
People who work together to complete project tasks.
People who have diverse skills and talents to complete tasks. It is important to recognize the strengths of your team members and assign tasks according to talents.
Key words and definitions
Team roles and responsibilities

## Slide 16
What is a
Team member?
People who work together to complete project tasks.
People who have diverse skills and talents to complete tasks. It is important to recognize the strengths of your team members and assign tasks according to talents.
Good project managers give tasks to their team members and trust them to do the work, supporting them along the way.
Key words and definitions
Team roles and responsibilities

## Slide 17
What is a Sponsor?
Key words and definitions
Team roles and responsibilities

## Slide 18
What is a Sponsor?
Key words and definitions
Team roles and responsibilities
An individual or organization that provides support and funding for a project.

## Slide 19
What is a Sponsor?
Key words and definitions
Team roles and responsibilities
Examples of sponsors include:
Board of Directors
Local businesses
School administrators
Stakeholders

## Slide 20
What is a Stakeholder?
Key words and definitions
Team roles and responsibilities

## Slide 21
What is a Stakeholder?
Key words and definitions
Team roles and responsibilities
People or organizations that have an interest in the project

## Slide 22
Key words and definitions
Team roles and responsibilities
Examples of stakeholders include:
Customers
Suppliers
Vendors
Team members
Project sponsors
What is a Stakeholder?

## Slide 23
Project Management Phases
FIVE PHASES OF PROJECT MANAGEMENT
INITIATING
PLANNING
EXECUTING
MONITORING, CONTROLLING & EVALUATION
CLOSING
Notes: More notes in facilitator guide:
In this training, we'll cover the five key phases of project management. These phases help guide a project from start to finish:
Initiating: This is where we define the project, its goals, and get approval to move forward.
Planning: Here, we create a detailed plan, outlining how the project will be carried out, including tasks, deadlines, and resources.
Executing: This is where the project gets done! Tasks are carried out, and team members work together to achieve goals.
Monitoring & Controlling: Throughout the project, we keep an eye on progress, checking for any issues or changes needed to stay on track.
Closing: Once everything is complete, we review the project to make sure all goals were met and officially close it.
We will walk through these phases one-by-one, starting with initiating…next…

## Slide 24
Project Management Phases
Progress is not linear

## Slide 25
Project Management Phases
FIVE PHASES OF PROJECT MANAGEMENT
INITIATING
PLANNING
EXECUTING
MONITORING, CONTROLLING & EVALUATION
CLOSING
Notes: More notes in facilitator guide:
In this training, we'll cover the five key phases of project management. These phases help guide a project from start to finish:
Initiating: This is where we define the project, its goals, and get approval to move forward.
Planning: Here, we create a detailed plan, outlining how the project will be carried out, including tasks, deadlines, and resources.
Executing: This is where the project gets done! Tasks are carried out, and team members work together to achieve goals.
Monitoring & Controlling: Throughout the project, we keep an eye on progress, checking for any issues or changes needed to stay on track.
Closing: Once everything is complete, we review the project to make sure all goals were met and officially close it.
We will walk through these phases one-by-one, starting with initiating…next…

## Slide 26
Enjoy a 15-minute break.

## Slide 27
FIVE PHASES OF PROJECT MANAGEMENT
Project Management Phases
INITIATING
PLANNING
EXECUTING
MONITORING, CONTROLLING & EVALUATION
CLOSING
This is where we define the project, its goals, and get approval to move forward.
Initiating

## Slide 28
This is where we define the project, its goals, and get approval to move forward.
Project Management Phases
INITIATING
Initiating
Notes: Let’s start with phase 1: Initiating

## Slide 29
Project Management Phases
INITIATING
During the Initiating Phase of project management, you will:
Determine the need your project will address or try to fix
Decide what product or service you want to create
Initiating
Notes: Initiating Phase
-----------
During the Initiating Phase of project management, you will:
Determine the need your project will address
Decide what you product or service you want to create
Assign a project manager
Many of you have already begun exploring the need to address in your community, but don’t worry we’ll go through 3 steps here, together, to help you determine a project that works for you and your community. Let’s go…
(Ask everyone to take out their completed assessment so the group can review the findings together. Walk through the questions, guiding pairs to complete or update their assessments as needed.)

## Slide 30
Project Idea
What are you passionate about? Be specific
(For example: helping others, education, sports, the environment, inclusion in schools, etc.)
What skills or strengths do you have? Be specific.
(For example: problem-solving, leadership, creativity, communication, teamwork, etc.)
Step 0
Know Your Strengths and Interests
Initiating
INITIATING

## Slide 31
Project Idea
Which area did you choose to study and think about improving?
» Special Olympics Program? » Community?
What positive things did you notice?
What problems or challenges did you see?
How did what you saw connect with the strengths, interests, and skills you wrote down in Step 0?
What did you see or experience that made you think this is a need or issue?
Step 1
Look at your community
Initiating
INITIATING

## Slide 32
 | Effects of problem | What happens because of the problem?
 | Problem | What is the main problem?
 | Causes of problem | Why does the problem exist?
Project Idea
INITIATING
Initiating

## Slide 33
 | Effects of problem | 
 | Problem | 
 | Causes of problem | 
Project Idea
INITIATING
Initiating

## Slide 34
 | Effects of problem | 
 | Problem | There are no Special Olympics activities in schools near me or in my area.
 | Causes of problem | 
Project Idea
INITIATING
Initiating

## Slide 35
 | Effects of problem | 
 | Problem | There are no Special Olympics activities in schools near me or in my area.
 | Causes of problem | School administrators don’t understand the benefits of Special Olympics programming. Teachers already have a lot to handle and don’t have time to take on another role.
Project Idea
INITIATING
Initiating

## Slide 36
 | Effects of problem | The school is not inclusive toward people with I/DD. Students with I/DD at this school have a negative school experience where teachers and students without I/DD have low expectations of them.
 | Problem | There are no Special Olympics activities in schools near me or in my area.
 | Causes of problem | School administrators don’t understand the benefits of Special Olympics programming. Teachers already have a lot to handle and don’t have time to take on another role.
Project Idea
INITIATING
Initiating

## Slide 37
Building my project idea
› I want to… (What do you want to do?)
› Because… (Why is it important to you?)
› I can do this through… (How will you do it?)
Pre-Training: “Building your Project Idea” Assessment
INITIATING

## Slide 38
Building my project idea
› I want to… (What do you want to do?)
› Because… (Why is it important to you?)
› I can do this through… (How will you do it?)
Pre-Training: “Building your Project Idea” Assessment
INITIATING
Right now, only 35% of our athletes are under 25. This is a problem because I know how much Special Olympics meant to me when I was younger and I want the next generation to experience the joy of Special Olympics at a young age.
I will recruit younger athletes by partnering with schools, community centers, and other sports programs.
I want to increase the number of Special Olympics athletes under the age of 25.

## Slide 39
Building my project idea
› I want to… (What do you want to do?)
› Because… (Why is it important to you?)
› I can do this through… (How will you do it?)
Pre-Training: “Building your Project Idea” Assessment
INITIATING
Workbook Activity
15 minutes

## Slide 40
“Are you sure” Project Idea Questions:
Do you have the resources, skills, and knowledge to handle this project?
Do you feel this project would be easy to track and measure success?
Are you confident you can tackle this project and help solve a community need?
Can you easily explain this need and project to others?
Does this need truly matter to your community?
Is completing this project realistic for you to complete?
INITIATING
Project Idea Questions
Are you sure?

## Slide 41
Workbook Activity
15 minutes
Project Idea Questions
Are you sure?
Write your Community Project Here: _ _ _ _ _ _ _ _ _ _ _ _ _ _
“Are you Sure” Project Idea Questions |  | Yes or no?
1. Do you have the resources, skills, and knowledge to handle this project? |  | 
2. Do you feel this project would be easy to track and measure success? |  | 
3. Are you confident you can tackle this project and help solve a community need? |  | 
4. Can you easily explain this need and project to others? |  | 
5. Does this need truly matter to your community? 6. Is this project realistic for you to complete? |  | 
INITIATING

## Slide 42
Project Ideas Presentation
INITIATING
Share your Project Ideas
Get Feedback

## Slide 43
We will reconvene on:
(date)
Steps 2-3 in the “Building Your Project Idea Assessment” require you to interview people in your Program or your community, sharing your project idea with them and asking them for feedback.
Complete those two steps now between Part 1 and Part 2 of this training. This should be your first priority.
Summarize your project idea by answering a series of questions under the “Finalizing my project idea” section on the previous page of the workbook.
Come to Part 2 of the training ready to share your project idea, and any updates and insights you learned during the break. Be ready to receive feedback and suggestions from your fellow athlete leaders.
Homework between Part 1 and Part 2
INITIATING

## Slide 44
PART 2:
PLANNING AND MANAGING YOUR PROJECT

## Slide 45
Project Idea
Who did you talk to?
What challenges did they mention?
Did they share any solutions or past experiences?
Step 2
Ask Around
Initiating
INITIATING

## Slide 46
Project Idea
What are two major needs or issues that need to be addressed, based on your findings from Steps 0, 1 & 2?
What are two ways you could help address these needs?
What is one action you can take that excites you, makes a difference, and helps solve a Program or community need?
Step 3
Final Reflection
Initiating
INITIATING

## Slide 47
What is the Program or Community need?
What will you do?
Why does it matter—to you and your community?
How will you do it?
When will you complete it?
Who will help? Who will benefit?
Who can help you? How can they help you?
Whom will this project help? How will it help them?
What is your Project?

## Slide 48
FIVE PHASES OF PROJECT MANAGEMENT
Project Management Phases
INITIATING
PLANNING
EXECUTING
MONITORING, CONTROLLING & EVALUATION
CLOSING
Here, we create a detailed plan of how the project will be done, including tasks, deadlines, and resources.
Planning
Notes: Hooray. Congratulations.
Now that learners have their project idea, we have completed initiating and will now move onto planning….

## Slide 49
Here, we create a detailed plan of how the project will be completed, including tasks, deadlines, and resources.
Project Management Phases
PLANNING
Planning
Notes: Planning: Here, we create a detailed plan, outlining how the project will be carried out, including tasks, deadlines, and resources.

## Slide 50
Project Management Phases
PLANNING
Planning
During the Planning Phase of project management, you will:
Determine the need your project will address
Decide what product or service you want to create
Assign a project manager
Notes: Planning: Here, we create a detailed plan, outlining how the project will be carried out, including tasks, deadlines, and resources.

## Slide 51
SMART GOALS
SMART GOALS
Project Management Phases - Planning
S | M | A | R | T
PLANNING

## Slide 52
SMART GOALS
Project Management Phases - Planning
S
Specific
What do I want to accomplish?
Why is this goal important?
Who is involved?
Where is it located?
What resources do I need to accomplish it?
Specific
S | M | A | R | T
PLANNING

## Slide 53
SMART GOALS
SMART GOALS
Project Management Phases - Planning
S | M | A | R | T
Specific |  |  |  | 
PLANNING

## Slide 54
SMART GOALS
Project Management Phases - Planning
M
Measurable
Measurable
How much?
How many?
How will I know when it’s complete?
S | M | A | R | T
PLANNING

## Slide 55
SMART GOALS
SMART GOALS
Project Management Phases - Planning
S | M | A | R | T
Specific | Measurable |  |  | 
PLANNING

## Slide 56
SMART GOALS
Project Management Phases - Planning
A
Achievable
Achievable
How can I accomplish my goal?
What resources or opportunities could help me?
Are there any obstacles, like time or money, that I need to consider?
S | M | A | R | T
PLANNING

## Slide 57
SMART GOALS
SMART GOALS
Project Management Phases - Planning
S | M | A | R | T
Specific | Measurable | Achievable |  | 
PLANNING

## Slide 58
SMART GOALS
Project Management Phases - Planning
R
Relevant
Relevant
Is it something that is important to me?
Does this goal matter to me?
Is this the right time for me to do this?
Am I the right person to take this on?
For group projects: Does this match what our team or community needs?
S | M | A | R | T
PLANNING

## Slide 59
SMART GOALS
SMART GOALS
Project Management Phases - Planning
S | M | A | R | T
Specific | Measurable | Achievable | Relevant | 
PLANNING

## Slide 60
SMART GOALS
Project Management Phases - Planning
T
Time-bound
Time-bound
When do I want to start this?
When do I want to achieve this?
What can I do today to move toward my goal?
What can I accomplish in six weeks?
Where do I want to be in four months?
S | M | A | R | T
PLANNING

## Slide 61
Project Management Phases
Planning
The two most important documents you need for your project are:
A short overview that briefly describes the projects' purpose, goals, steps, outcomes, used as a quick reference for stakeholder updates.
A detailed document outlining the objectives, scope, timeline, tasks, resources, and risk of a project, serving as a roadmap to implement your project.
Project Summary
Project Plan
PLANNING

## Slide 62
PROJECT NAME |  | PROJECT NAME |  |  |  |  |  | 
 |  | Project Manager | Project Manager name |  |  |  |  | 
 |  | Teammates | Teammate names |  |  |  |  | 
 | The Problem | The Problem |  |  |  |  |  | 
 |  | What is a big barrier to inclusion in your community that you are trying to solve through your project? |  |  |  |  |  | 
 | Project Activities | Project Activities |  |  |  | The Impact |  | 
 | Describe how your project will work | Describe how your project will work What do I want to accomplish? Where will your project take place? Who will be involved? |  |  |  | Describe what you hope to achieve with your project |  | 
Project Summary
PLANNING
Notes: Ask participants to look at their participant workbook and complete their own project summary.

## Slide 63
Project Name |  | PROJECT NAME | Recruiting and Empowering Athletes |  |  |  |  |  | 
 |  | Project Manager |  |  |  |  |  |  | 
 |  | Teammates | Conal, Cristina, Caitlin and Brandon |  |  |  |  |  | 
 | The Problem | The Problem |  |  |  |  |  |  | 
 |  | What is a big barrier to inclusion in your community that you are trying to solve through your project? |  |  |  |  |  |  | 
 | Project Activities | Project Activities |  |  |  |  | The Impact |  | 
 |  | Describe how your project will work What do I want to accomplish? Where will your project take place? Who will be involved? |  |  |  |  |  |  | 
 | Project Name |  | 
 | Project Manager |  | 
 | Teammates |  | 
Example of Project Summary
Recruiting and Empowering Athletes
Conal, Cristina, Caitlin and Brandon
PLANNING
Conal

## Slide 64
Project Name |  | PROJECT NAME | Recruiting and Empowering Athletes |  |  |  |  |  | 
 |  | Project Manager |  |  |  |  |  |  | 
 |  | Teammates | Conal, Cristina, Caitlin and Brandon |  |  |  |  |  | 
 | The Problem | The Problem |  |  |  |  |  |  | 
 |  | What is a big barrier to inclusion in your community that you are trying to solve through your project? |  |  |  |  |  |  | 
 | Project Activities | Project Activities |  |  |  |  | The Impact |  | 
 |  | Describe how your project will work What do I want to accomplish? Where will your project take place? Who will be involved? |  |  |  |  |  |  | 
Example of Project Summary
PLANNING
 | The Problem |  |  | 
Not enough athletes (under 25) participating in our Program.
Challenges
Lack of awareness / recruitment of athletes and coaches.
 | Project Name |  | 
 | Project Manager |  | 
 | Teammates |  | 
Recruiting and Empowering Athletes
Conal, Cristina, Caitlin and Brandon
Conal
Solution
Launch an engagement initiative that includes outreach events, mentorship from current athletes, and leadership training for new recruits

## Slide 65
Project Name |  | PROJECT NAME | Recruiting and Empowering Athletes |  |  |  |  |  | 
 |  | Project Manager |  |  |  |  |  |  | 
 |  | Teammates | Conal, Cristina, Caitlin and Brandon |  |  |  |  |  | 
 | The Problem | The Problem |  |  |  |  |  |  | 
 |  | What is a big barrier to inclusion in your community that you are trying to solve through your project? |  |  |  |  |  |  | 
 | Project Activities | Project Activities |  |  |  |  | The Impact |  | 
 |  | Describe how your project will work What do I want to accomplish? Where will your project take place? Who will be involved? |  |  |  |  |  |  | 
Example of Project Summary
PLANNING
 | The Problem |  |  | 
Not enough athletes (under 25) participating in our Program.
 | Project Name |  | 
 | Project Manager |  | 
 | Teammates |  | 
Recruiting and Empowering Athletes
Conal, Cristina, Caitlin and Brandon
Conal
Challenges
Lack of awareness / recruitment of athletes and coaches.
Solution
Launch an engagement initiative that includes outreach events, mentorship from current athletes, and leadership training for new recruits
 | Project Activities |  | 
What will you do?
Event in the community to raise awareness and create excitement.
Where will your project take place?
At a school or community event
Who will be involved?
Mentors, teachers, athletes, myself

## Slide 66
Example of Project Summary
PLANNING
 | The Problem |  |  | 
Not enough athletes (under 25) participating in our Program.
Challenges
Lack of awareness / recruitment of athletes and coaches.
Solution
Launch an engagement initiative that includes outreach events, mentorship from current athletes, and leadership training for new recruits
 | Project Name |  | 
 | Project Manager |  | 
 | Teammates |  | 
Recruiting and Empowering Athletes
Conal, Cristina, Caitlin and Brandon
Conal
 | Project Activities |  | 
What do I want to accomplish?
Event in the community to raise awareness and create excitement.
Where will your project take place?
At a school or community event
Who will be involved?
Mentors, teachers, athletes, myself
 | The Impact | 
What would the result of your project be?
Increase in athletes under 25 from 35% to 50%
How will you evaluate your project?
Compare numbers of athletes under 25 over 5 years.
How will you make it sustainable?
Peer mentorship program

## Slide 67
Example of Project Summary
PLANNING
 | The Problem |  |  | 
Not enough athletes (under 25) participating in our Program.
Challenges
Lack of awareness / recruitment of athletes and coaches.
Solution
Launch an engagement initiative that includes outreach events, mentorship from current athletes, and leadership training for new recruits
 | Project Name |  | 
 | Project Manager |  | 
 | Teammates |  | 
Recruiting and Empowering Athletes
Conal, Cristina, Caitlin and Brandon
Conal
 | Project Activities |  | 
What do I want to accomplish?
Event in the community to raise awareness and create excitement.
Where will your project take place?
At a school or community event.
Who will be involved?
Mentors, teachers, athletes, myself
 | The Impact | 
What would the result of your project be?
Increase in athletes under 25 from 35% to 50%
How will you evaluate your project?
Compare numbers of athletes under 25 over 5 years.
How will you make it sustainable?
Peer mentorship program.

## Slide 68
 |  | Project Name |  |  |  |  |  |  |  |  | 
 |  | Project Manager |  |  |  |  |  |  |  |  | 
 |  | Teammates |  | Teammate names |  |  |  |  |  |  | 
 | The Problem | The Problem |  |  |  |  |  |  |  |  | 
 |  | What is a big barrier to inclusion in your community that you are trying to solve through your project? |  |  |  |  |  |  |  |  | 
 | Project Activities | Project Activities |  |  |  |  | The Impact |  |  |  | 
 |  | Describe how your project will work What do I want to accomplish? Where will your project take place? Who will be involved? |  |  |  |  |  |  |  |  | 
Project Summary
Workbook Activity
15 minutes
PLANNING

## Slide 69
Enjoy a 15-minute break.

## Slide 70
PLANNING
Project Management Phases
Planning
The two most important documents you need for your project are:
Overview that briefly describes the projects' purpose, goals, steps, outcomes, used as a quick reference for stakeholder updates.
A detailed document outlining the objectives, scope, timeline, tasks, resources, and risk of a project, serving as a roadmap to implement your project.
Project Summary
Project Plan

## Slide 71
Complete? | Status | Activity/Task | Start date | End date | Owner | Helpers | Notes
Project Plan
PLANNING

## Slide 72
Project Management Phases
Planning
Traffic Light System
PLANNING
Green
The project or task is on track, progressing as planned, with no major issues.
Yellow
There are some challenges or delays, but the project can still be completed with adjustments.
Red
The project is at risk or stalled due to significant problems that require immediate action.

## Slide 73
Example of Project Plan
Complete? | Status | Activity/Task | Start date | End date | Owner | Helpers | Notes
 |  | Choose Teammates | Aug. 1, 2022 | Oct. 31, 2022 | Conal | N/A | Brandon, Caitlin, Cristina selected for team
 |  | Identify Mentor | Nov. 1, 2022 | Nov. 15, 2022 | Conal | N/A | Emily selected as mentor
 |  | Assign roles | Nov. 1, 2022 | Nov. 15, 2022 | Cristina | Brandon, Conal, Caitlin | Conal and Caitlin confirmed their role, but waiting for Brandon to confirm his
 |  | Decide on budget | Nov. 15, 2022 | Dec. 1, 2022 | Caitlin | Brandon, Conal, Cristina | Waiting for project funds to be released
 |  | Make initial contact with school | Nov. 15, 2022 | Dec. 1, 2022 | Brandon | N/A | Email was sent to the school – waiting on response
PLANNING

## Slide 74
Complete? | Status | Activity/Task | Start date | End date | Owner | Helpers | Notes
Project Plan
PLANNING
Workbook Activity
15 minutes

## Slide 75
FIVE PHASES OF PROJECT MANAGEMENT
Project Management Phases
MONITORING, CONTROLLING & EVALUATION
Executing
INITIATING
PLANNING
EXECUTING
CLOSING

## Slide 76
Project Management Phases
This is where the project gets done! Tasks are carried out, and team members work together to achieve goals.
Executing
EXECUTING
Notes: Executing: This is where the project gets done! Tasks are carried out, and team members work together to achieve goals.

## Slide 77
Project Management Phases
Executing
EXECUTING
During the Executing Phase of project management, you will:
Begin working on assigned tasks
Share regular updates with the team, stakeholders, sponsor
Adjust your project plan as needed

## Slide 78
Project Management Phases
Executing
EXECUTING
Three things that will help you execute your tasks better:
Setting and sticking to a consistent routine
Good communication between you and others
Documenting everything that happens

## Slide 79
Setting and sticking to a consistent routine
Good communication between you and others
Documenting everything that happens
v
Project Management Phases
Executing
EXECUTING
Set up a routine of checking your project plan on a regular basis.
A good routine:
Helps you stay on track and ensures progress
Breaks tasks into smaller steps and set deadlines
Ensures you and your team are not forgetting anything.

## Slide 80
Good communication between you and others
Documenting everything that happens
v
Project Management Phases
Executing
EXECUTING
Keep everyone informed about progress, changes, and challenges.
Use regular check-ins, emails, or meetings to ensure alignment.
Be clear, concise, and proactive in asking for help or offering updates.

## Slide 81
Documenting everything that happens
v
Project Management Phases
Executing
EXECUTING
Keep records of decisions, changes, and completed tasks to track progress.
Documentation helps solve problems, maintain accountability, and improve future projects.
Use tools like notebooks, digital trackers, or project management software to stay organized. (Smartsheet, excel, google sheets, Teams, etc. )

## Slide 82
As a Project Manager,
What are three ways you will document your project work?
What are some ideas for document?
Reflection

## Slide 83
Project Management Phases
MONITORING, CONTROLLING & EVALUATION
Throughout the project, we keep an eye on progress, checking for any issues or changes needed to stay on track.
INITIATING
PLANNING
EXECUTING
CLOSING
Monitoring, Controlling & Evaluation

## Slide 84
Project Management Phases
MONITORING, CONTROLLING & EVALUATION
Throughout the project, we keep an eye on progress, checking for any issues or changes needed to stay on track.
Monitoring, Controlling & Evaluation

## Slide 85
Project Management Phases
MONITORING, CONTROLLING & EVALUATION
During the Monitoring, Controlling & Evaluation Phase of project management, you will:
Review and track the progress of the project
Manage project issues
Assess risks
Monitoring, Controlling & Evaluation

## Slide 86
Project Management Phases
MONITORING, CONTROLLING & EVALUATION
Risks are problems that could happen in the future.
Monitoring, Controlling & Evaluation
Define Risks and Issues
Example: A key team member might leave before the project is done.
Issues are problems that are already happening
Example: The venue you booked for an event just canceled on you.

## Slide 87
Project Management Phases
MONITORING, CONTROLLING & EVALUATION
Monitoring, Controlling & Evaluation
How to plan for risks?
Think Ahead – What could go wrong?
Sort Them – Is it a risk or an issue?
  Risk = might happen | Issue = already happening
Find Solutions – How can we prevent or fix them?
By thinking ahead, you’ll be ready to handle challenges and keep your project on track!

## Slide 88
Low | Medium | High | Extreme
Snooze. No big deal, continue as planned. | Thinking? Consider taking some action to reduce risk. | Yikes. Get help and adjust your plan. | Full uh-oh. May need to pause or rethink the project.
Risk Analysis
Question: “How big is the risk?”
MONITORING, CONTROLLING & EVALUATION
Risk Rating System

## Slide 89
FIVE PHASES OF PROJECT MANAGEMENT
Project Management Phases
MONITORING, CONTROLLING & EVALUATION
Closing
INITIATING
PLANNING
EXECUTING
CLOSING
Notes: Finally, let’s explore Closing….

## Slide 90
Project Management Phases
Review the project to make sure all goals were met and officially close it.
Closing
CLOSING

## Slide 91
Project Management Phases
Closing
CLOSING
During the Closing of project management, you will:
Document what you learned
Complete any remaining requirements
Create a report to share what you accomplished
Celebrate with your team

## Slide 92
Look at your project schedule.
Have you checked off all your tasks?
Review to see what is still missing.
What needs to be completed?
CLOSING
Finalize Your Project Plan and Schedule
Project Management Phases
Closing

## Slide 93
Send thank-you notes, give shout-outs, or celebrate together.
CLOSING
Show Appreciation
Project Management Phases
Closing

## Slide 94
Telling
the story of your project is important
Your project stories are powerful, meaningful and worth sharing.
Your project stories show the big moments and the teamwork.
Your project stories also show the strength in facing challenges and problem solving.
Your project stories help others understand and support you and your project.
Your project stories inspire others to keep the project going and either build upon it or do something similar in their own area.
CLOSING
Project Management Phases
Closing

## Slide 95
Why share your Project?
Creates connection
Builds Empathy
Helps Others Understand “Why”
Inspires other to take action
Invites others to listen
Shows Impact
CLOSING
Project Management Phases
Closing

## Slide 96
Telling a Powerful Story…
CLOSING
Project Management Phases
Closing
It explains…
What the problem was
What you did
What changed because of it
It communicates real people and real experiences…

## Slide 97
Reflection
CLOSING
› What was the challenge or need? Example: “There aren’t enough coaches for young athletes in my community.” |  | 
Write your own |  | 
› What did you (or someone else) do to help? Example: “I started a plan to recruit new coaches by visiting schools and talking to teachers.” |  | 
Write your own |  | 
› What changed because of that action? Example: “Three new coaches signed up, and now we can start a new soccer team for younger athletes.” |  | 
Write your own |  | 
› What real-life experience or emotion could you include to help people care? (Don’t share names or private info—just focus on how it felt or what happened.) Example: “One student with disabilities said it was the first time they felt included on a team.” |  | 
Write your own |  | 
Activity: Build Your Story

## Slide 98
Sharing your Project
Public Speaking
Things to remember:
Project Management Phases - Closing
Be confident
Emphasize Words
Watch your body language
Keep Calm

## Slide 99
Sharing your Project
Public Speaking Group Activity
Project Management Phases - Closing
We need 2 – 3 volunteers to share your project story, from the previous activity, with the group.
The challenge or need
Why you did to help
what changed because of that action
A real-life feeling or experience you can share
Instructions for the Group:
As you listen, use the 4 public speaking tips to give helpful and kind feedback.
Be confident – Did the speaker believe in their message? Did they look comfortable?
Emphasize words – Did they use their voice to highlight the most important parts of their story?
Watch your body language – Did they make eye contact, use hand gestures, or tell the story instead of reading the story?
Keep calm – Did they keep going even if they forgot something or make a mistake?

## Slide 100
After sharing your project, take time to reflect.
Listen to feedback from the audience and other speakers.
Ask yourself:
What went well?
What could I do better next time?
Make notes to help you grow as a presenter and improve your project.
Practice sharing your project again
After You Share: Practice and Improve
Feedback is a gift

## Slide 101
Where to share your Project Story?
CLOSING
Project Management Phases
Closing
What are the most common places for athlete leaders to share their story?
Think about your project, who are the people who could help your project make a larger impact?
Where do you think you could share your project?

## Slide 102
THANK YOU!
PROJECT MANAGEMENT
TRAINING FOR ATHLETE LEADERS
Please take the evaluation: http://bit.ly/3NtXZ0C